## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 |  | Choose the data file with at least 2 crypto currencies | MUST HAVE |  | vignan | 3- Completed
1 | 1 |  | Store the data in the database | SHOULD HAVE |  | vignan | 3- Completed
1 | 1 |  | Calculate the metrics for the data and store in the data frame. | MUST HAVE |  | vignan | 3- Completed
1 | 1 |  | Apply parallel tasks concepts to the above steps | MUST HAVE |  | vignan | 3- Completed
2 | 2 |  | Assign weights for the portfolio and Check if weights are assigned based on the rule,Calculate portfolio return,Calculate portfolio risk | MUST HAVE |  | vignan | 3- Completed
2 | 2 |  | Create two tables for portfolio and portfolio_assets to store currencies, weights,, returns, risk, metrics | MUST HAVE |  | vignan | 3- Completed
2 | 2 |  | Extend logic: run multiple rule tests in parallel (ThreadPool). | MUST HAVE |  | vignan | 3- Completed
2 | 2 |  | Compare portfolio return vs. single asset return with some sample data and plot the graph | MUST HAVE |  | vignan | 3- Completed
3 | 3 |  | Implement rules to identify the risk , store them in database and send email alert if anyone fails | MUST HAVE |  | vignan | 3- Completed
3 | 3 |  | Predict both portfolio and individual returns using linear regression model | MUST HAVE |  | vignan | 3- Completed
4 | 4 |  | Implement rule setter and calculate portfolio returns, store in Database | SHOULD HAVE |  | vignan | 3- Completed
4 | 4 |  | Apply stress test and see how portfolio returns behave | MUST HAVE |  | vignan | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
1 | 1 | Choose the data file with at least 2 crypto currencies | 19/08/25 | 29/08/25 | vignan | Build | 3- Completed | 1
2 | 2 | Store the data in the database | 19/08/25 | 29/08/25 | vignan | Coding | 3- Completed | 1
3 | 3 | Calculate the metrics for the data and store in the data frame. | 19/08/25 | 29/08/25 | vignan | Coding | 3- Completed | 2
4 | 4 | Apply parallel tasks concepts to the above steps | 19/08/25 | 29/08/25 | vignan | Coding | 3- Completed | 3
SPRINT 2 BACKLOG
5 | 5 | Assign weights for the portfolio and Check if weights are assigned based on the rule,Calculate portfolio return,Calculate portfolio risk | 2025-01-09 | 2025-12-09 | vignan | Coding | 3- Completed | 4
6 | 6 | Create two tables for portfolio and portfolio_assets to store currencies, weights,, returns, risk, metrics | 2025-01-09 | 2025-12-09 | vignan | Build | 3- Completed | 2
7 | 7 | Extend logic: run multiple rule tests in parallel (ThreadPool). | 2025-01-09 | 2025-12-09 | vignan | Coding | 3- Completed | 2
8 | 8 | Compare portfolio return vs. single asset return with some sample data and plot the graph | 2025-01-09 | 2025-12-09 | vignan | Unit Test | 3- Completed | 2
SPRINT 3 BACKLOG
9 | 9 | Implement rules to identify the risk , store them in database and send email alert if anyone fails | 15/09/25 | 27/09/25 | VIGNAN | Coding | 3- Completed | 2
10 | 10 | Predict both portfolio and individual returns using linear regression model | 15/09/25 | 27/09/25 | vignan | Design | 3- Completed | 2
SPRINT 4 BACKLOG
11 | 11 | Implement rule setter and calculate portfolio returns, store in Database | 29/09/25 | 2025-04-10 | vignan | Coding | 3- Completed | 3
12 | 12 | Apply stress test and see how portfolio returns behave | 29/09/25 | 2025-04-10 | vignan | Coding | 3- Completed | 2

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 1 | Discussed about the project | strictly listened to the explanation of mentor
1 | 2 | breifly discussed about the coins | listened to the explanation of mentor
1 | 3 | how to filter crypto coins | filtered the crypto coins
1 | 4 | how to download all the important files needed for project | downloaded later
1 | 5
1 | 6
1 | 7

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 14/08/25 | 29/08/25 | vignan | 16/08/25 | 28/08/25 |  | milestone 1 completed
2 | 2 | 31/08/25 | 2025-12-09 | vignan | 2025-01-09 | 2025-11-09 |  | milestone 2 completed
3 | 3 | 14/09/25 | 26/09/25 | vignan | 15/09/25 | 25/09/25 |  | milestone 3 completed
4 | 4 | 28/09/25 | 2025-04-10 | vignan | 29/09/25 | 2025-04-10 |  | milestone 4 completed