## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | 2025-08-29 | 2025-08-29 | to take atleast 2 datasets and calculate the metrics for the assigned data and apply parallel tasks | small dataset | vignan | Standards | yes | 2025-08-29 | closed
2 | 2025-08-29 | 2025-08-29 | to correct the metric calculations | adjusting calculations | vignan | Logical | yes | 2025-08-29 | closed
3 | 2025-09-12 | 2025-09-08 | to make the plot of portfolio analysis as line graph instead of bar graph | changing graph plot | vignan | User Interface | yes | 2025-09-08 | closed
4 | 2025-09-12 | 2025-09-09 | to check if rules are applied | rules are applied | vignan | Logical | yes | 2025-09-09 | closed
5 | 2025-09-12 | 2025-09-09 | risk rules threshold should not be crossed | values are cutoff to threshold | vignan | Logical | yes | 2025-09-09 | closed
6 | 2025-09-12 | 2025-09-10 | some changes should be made in md document | changes were made | vignan | Maintainability | yes | 2025-09-10 | closed
7 | 2025-09-26 | 2025-09-23 | adding mse and r square in linear regression | mse and r sq were added | vignan | Logical | yes | 2025-09-23 | closed
8 | 2025-09-26 | 2025-09-23 | apply more risk rules to the code | risk rules were added | vignan | Standards | yes | 2025-09-23 | closed
9 | 2025-10-04 | 2025-10-04 | need to apply dynamic weights for risk parity rule | dynamic weights were added | vignan | Standards | yes | 2025-10-04 | closed
10 | 2025-10-04 | 2025-10-04 | need to apply the weights based on the data present | adjustment in weights | vignan | Standards | yes | 2025-10-04 | closed
11 | 2025-10-04 | 2025-10-04 | Insights should be properly noted | Insights were noted | vignan | Logical | yes | 2025-10-04 | closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others